Organization: Health Access Network(HAN)
Grant Type: Health Promotion Grant
Funder: Global Health Partners

Project Title: “Preventive Health Workshops for Low-Income Communities”

Executive Summary:
Health Access Network seeks $110,000 to implement a preventive health education program for 500 low-income families, focusing on nutrition, hygiene, and chronic disease prevention.

Goals & Objectives:

- Conduct 30 workshops for 500 families by December 2025.

- Distribute educational materials and hygiene kits to all participants.

- Train 20 community health volunteers to continue program outreach.

Program Narrative:
The project delivers interactive workshops and practical demonstrations. Health volunteers engage families in hands-on activities, monitoring, and follow-up support to reinforce behavior change.

Budget Summary:

- Personnel: $55,000

- Materials & Supplies: $25,000

- Workshops & Community Outreach: $20,000

- Administration & Evaluation: $10,000

Evaluation & Reporting:

- Workshop attendance and participation logs

- Pre- and post-intervention surveys on knowledge and behavior

- Volunteer performance tracking

Sustainability:

- Trained volunteers continue outreach after grant period.

- Partnerships with local clinics integrate workshops into ongoing community health programs.